## Test Cases
test_id | business_requirement | scenario | precondition | steps | expected_result | actual_result | status | evidence | notes
UAT-001 | BR-001 | Executive ROAS reconciles | Green dbt build | Compare channel mart revenue divided by spend to report card | Values match governed formula |  | NOT RUN |  | Automatable
UAT-002 | BR-001 | CAC reconciles | Green dbt build | Compare spend divided by closed-won conversions | CAC matches governed formula and zero denominators are blank |  | NOT RUN |  | Automatable
UAT-003 | BR-001 | Channel totals reconcile | Semantic export loaded | Sum channels and compare to warehouse | Spend revenue and conversions match |  | NOT RUN |  | Automatable
UAT-004 | BR-001 | Date filter scope | Power BI report open | Select one reporting month | All dependent visuals show only selected month |  | NOT RUN |  | GUI
UAT-005 | BR-001 | Channel filter scope | Power BI report open | Select one channel | Campaign funnel target and quality visuals respond as designed |  | NOT RUN |  | GUI
UAT-006 | BR-002 | SCALE threshold | Action mart built | Inspect row above target multiplier | Action is SCALE with transparent reason |  | NOT RUN |  | Automatable
UAT-007 | BR-013 | REDUCE threshold | Action mart built | Inspect high-spend row below target multiplier | Action is REDUCE with P1 priority |  | NOT RUN |  | Automatable
UAT-008 | BR-013 | Funnel repair rule | Action mart built | Inspect below-target row with zero conversions | Action is FIX FUNNEL |  | NOT RUN |  | Automatable
UAT-009 | BR-013 | Missing target rule | Action mart built | Inspect campaign without matched target | Action is REVIEW TARGET |  | NOT RUN |  | Automatable
UAT-010 | BR-012 | Quality hold override | Fixture has missing campaign ID | Run action rules | DATA QUALITY HOLD overrides performance action |  | NOT RUN |  | Automatable
UAT-011 | BR-004 | ROAS absolute variance | Two complete periods exist | Subtract prior ROAS from current | Stored absolute variance matches |  | NOT RUN |  | Automatable
UAT-012 | BR-004 | ROAS percentage variance | Nonzero prior ROAS exists | Divide absolute variance by prior | Stored percentage variance matches |  | NOT RUN |  | Automatable
UAT-013 | BR-004 | No prior period | First period exists | Inspect driver row | Severity is INFO and driver is NO_PRIOR_PERIOD |  | NOT RUN |  | Automatable
UAT-014 | BR-004 | High severity threshold | Fixture changes ROAS by at least 25 percent | Build driver output | Severity is HIGH |  | NOT RUN |  | Automatable
UAT-015 | BR-004 | CAC absolute variance | Two complete periods exist | Subtract prior CAC from current | Stored absolute variance matches |  | NOT RUN |  | Automatable
UAT-016 | BR-004 | CAC zero denominator | No conversions for period | Calculate CAC | CAC is null rather than infinity or error |  | NOT RUN |  | Automatable
UAT-017 | BR-007 | GA4 event contract | GA4 fixture available | Validate required fields and accepted event names | Valid fixture passes |  | NOT RUN |  | Automatable
UAT-018 | BR-007 | Invalid GA4 event | Fixture contains unknown event | Run validator | Row is rejected with known_ga4_event rule |  | NOT RUN |  | Automatable
UAT-019 | BR-007 | Revenue event rule | Non-purchase row has revenue | Run validator | Row is rejected with revenue_only_on_purchase |  | NOT RUN |  | Automatable
UAT-020 | BR-008 | Live hostname exclusion | Daily BigQuery export available | Run bounded live selector | Approved hostname remains and localhost is excluded |  | NOT RUN |  | Automatable
UAT-021 | BR-009 | Ecommerce item grain | GA4 items model built | Compare item rows to unnested source arrays | Item rows reconcile without inflating events |  | NOT RUN |  | Automatable
UAT-022 | BR-007 | Funnel filter behavior | Power BI GA4 page open | Filter device and source | Funnel updates without cross-filter ambiguity |  | NOT RUN |  | GUI
UAT-023 | BR-003 | Spend attainment | Targets and actuals loaded | Divide actual spend by target spend | Attainment matches mart |  | NOT RUN |  | Automatable
UAT-024 | BR-003 | Revenue attainment | Targets and actuals loaded | Divide actual revenue by target revenue | Attainment matches mart |  | NOT RUN |  | Automatable
UAT-025 | BR-003 | Missing target visibility | Actual has no target | Open report | Missing target is visible and not treated as zero target |  | NOT RUN |  | GUI
UAT-026 | BR-010 | Attribution weights reconcile | Attribution fact built | Sum weights by conversion and model | Weights equal one within tolerance |  | NOT RUN |  | Automatable
UAT-027 | BR-010 | Attributed revenue reconciles | Attribution fact built | Sum attributed revenue by model | Each model reconciles to conversion revenue |  | NOT RUN |  | Automatable
UAT-028 | BR-010 | Model filter behavior | Attribution page open | Select each model | Visual and totals switch to selected model |  | NOT RUN |  | GUI
UAT-029 | BR-011 | Stale source warning | Fixture timestamp exceeds freshness SLA | Build source health | Source is marked stale or freshness failure |  | NOT RUN |  | Automatable
UAT-030 | BR-005 | Anomaly evidence | Material KPI deviation exists | Run transparent detector | Metric baseline deviation severity method and evidence are present |  | NOT RUN |  | Automatable
UAT-031 | BR-014 | Governed scenario set | Scenario inputs valid | Run standard scenarios | Baseline Conservative Expected Aggressive and User Defined are returned |  | NOT RUN |  | Automatable
UAT-032 | BR-015 | Scenario equation reconciliation | Allocations sum to one | Recalculate projected funnel and financial outputs | Results match zero-safe deterministic equations |  | NOT RUN |  | Automatable
UAT-033 | BR-020 | Source-to-landing reconciliation | Generated and ingestion manifests available | Compare source row counts to landed counts | All available checks meet recorded tolerance |  | NOT RUN |  | Automatable
UAT-034 | BR-022 | Bounded BigQuery configuration | Live selector configured | Inspect lookback and maximum-bytes safeguards | Cost guardrails remain explicit |  | NOT RUN |  | Automatable
UAT-035 | BR-020 | dbt-to-BI reconciliation | Mart and BI exports available | Compare row and financial totals | All available checks meet recorded tolerance |  | NOT RUN |  | Automatable
UAT-036 | BR-021 | Deterministic insight packet | Pipeline evidence available | Generate decision intelligence | Packet includes KPIs anomalies drivers actions scenarios warnings and references |  | NOT RUN |  | Automatable
UAT-037 | BR-013 | Priority sorting | Action mart loaded | Sort P0 through P3 | Quality holds and material underperformance appear first |  | NOT RUN |  | Automatable
UAT-038 | BR-013 | Action reason visibility | Power BI action page open | Select campaign | Action reason supporting metric and monitor metric are visible |  | NOT RUN |  | GUI
UAT-039 | BR-017 | Power BI refresh | Report assembled and credentials configured | Trigger refresh | Refresh completes and timestamp advances |  | NOT RUN |  | GUI credentials required
UAT-040 | BR-017 | RLS validation | Power BI roles configured | Use Test as role for each role | Each role sees only intended rows and no restricted raw data |  | NOT RUN |  | GUI

## Test Plan
P2 Modeled UAT Test Plan
These acceptance cases are repository-authored. They do not claim execution by real stakeholders.
Area | Scope | Execution Type | Entry Criteria | Exit Criteria | Current Classification
KPI reconciliation | Spend, revenue, ROAS, CAC, funnel and targets | Automated + analyst review | Green data build | Tolerance checks pass | Repository validation
Analytics | Variance, anomaly, attribution and scenarios | Automated | Governed marts available | Rules and equations pass | Repository validation
Power BI behavior | Filters, navigation, drill-through, tooltips | Power BI Desktop GUI | Report assembled | Expected cross-filter/navigation behavior | NOT EXECUTED
RLS | Executive, Channel Manager, Regional Manager | Static + Power BI View-as | Roles imported | Role predicates verified at runtime | Static validation only
Live GA4 | Hostname exclusion, sessions, items and funnel | Bounded BigQuery/dbt | Daily export available | Approved selector/tests pass | Live evidence documented
Release quality | Freshness, rejected rows, reconciliation, security | Automated | Evidence generated | No failed release control | Repository validation

## Coverage Summary
UAT Coverage Summary
Formula-driven counts. A NOT RUN case is not represented as stakeholder acceptance.
Metric | Count | Meaning
Total cases | 40 | Existing strengthened package
Automatable notes | 32 | Cases tagged Automatable
GUI notes | 8 | Cases requiring a BI interface
Not run | 40 | No user execution claimed